## Planner
The 2027 Pinch Point Planner
One page. About an hour. A clear view of where next year's pinch points are going to be.
How to use it
1. List what cannot move | The dates you cannot control: shows you exhibit at, your own event, launches, year end, renewal or recruitment windows, board reporting.
2. Shade the run-up, not the date | Type R in every month of preparation and follow-up. Type X in the month it actually happens. The colour fills in on its own.
3. Name an owner, then be honest | In that specific week, alongside everything already committed, will your team have the time and resources to deliver? Flag anything that needs support.
4. Look for collisions and the gap | Where two run-ups overlap is your pinch point. The quiet stretch is where work with no external deadline can finally get finished.
Pinch points needing support: | 1 | Counts every row where the last column is set to Yes.
Fixed point | Date | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | Owner | Support needed?
e.g. Annual conference | 1 Date: 14 May; Counts every row where the last column is set to Yes. Mar: R; Counts every row where the last column is set to Yes. Apr: R; Counts every row where the last column is set to Yes. May: X; Counts every row where the last column is set to Yes. Jun: R; Counts every row where the last column is set to Yes. Owner: Marketing lead | Yes
Key: | 1 Date: R; Counts every row where the last column is set to Yes. Jan: Run-up: preparation before, follow-up after; Counts every row where the last column is set to Yes. Jul: X; Counts every row where the last column is set to Yes. Aug: The date itself. Type into the white cells only. See the Lead times tab before you finish.

## Lead times
Before you finish the plan
What things actually take |  | Three questions for every pinch point
Work backwards from the date you want it live, not forwards from January. |  | Ask these of each shaded block on the Planner tab.
What you want to start | Realistic lead time | Does the team genuinely have the capacity?
Podcast, concept to first episode | 8 to 12 weeks | In that specific week, alongside everything already committed, will your team have the time and resources to deliver?
Content programme, before first publication | About a quarter
Integrated campaign | 6 to 8 weeks | Is this the best use of their time?
Trade show or exhibition | 8 weeks before, 3 weeks after | Some work truly needs the people who know the organisation inside out. Plenty of it does not, and handing it to them anyway can be expensive.
Renewal or recruitment window | 6 weeks of preparation
A well-run event | 6 to 9 months | What happens if it slips?
Rebrand or new website build | 6 months and upwards | Some things can move a fortnight with no consequence at all. Others cannot move by a day. That split tells you where outside support is worth paying for.
Working backwards: say you want the first podcast episode live in March. Eight to twelve weeks of lead time puts the start before Christmas. Is there enough time to do it to a high standard? If not, can it move, or does that planning meeting need to happen now?
What has to be decided before January
Anything you want live in the early part of the year. Work backwards from the date. Is there enough time to get it done to a high standard? If not, can it move, or does that planning meeting need to happen now?
Anything that needs money. Including a line for flexible project support while the budget is still in draft is far easier than finding the funds in June, when the pressure has already arrived and everyone is busy.
Stuck on one of them? Dovetail Creative works on a project basis around the pinch points: marketing, events, membership and podcast production. dovetailcreative.co.uk/contact